## Scoring
Sample ChatGPT-Web Stories and Bugs | Users | Often | Bad | User Need Score | Dev Cost (Story Points) | WSJF | Order for Development | Instructions
1. The Chrome Back button does not take you "Back" | 3 - All | 3 | 4 - Critical | 36 | 43 | 0.83721 | 8 | This is a sample of stories or bugs.
2. Text: "Run" should be called "Search" in the UI | 3 - All | 3 - All of the time | 2 - Important | 18 | 3 | 6 | 1 | 1. Enter your own table of stories and bugs
3. You can't submit a prompt by pressing return in a field | 3 - All | 3 - All of the time | 2 - Important | 18 | 20 | 0.9 | 7 | 2. Understand each story
4. Vertical scroll bar is missing from the Conversational UI | 2 - Some | 3 - All of the time | 3 - Severe | 18 | 14 | 1.2857 | 4 | 3. Discuss and understand the stories with your team
5. "Enterprise Support Recommendations" is a confusing term | 2 - Some | 3 - All of the time | 2 - Important | 12 | 4 | 3 | 2 | 4. Independentely score each story
6. Columns are not sorted correctly | 2 - Some | 3 - All of the time | 2 - Important | 12 | 10 | 1.2 | 5 | 5. Review, compare and come to common score
7. The website and default chat language do not match | 2 - Some | 3 - All of the time | 2 - Important | 12 | 12 | 1 | 6 | 6. Get the dev cost from development.
8. Formatted numbers and text labels should align correctly | 3 - All | 3 - All of the time | 1 - Not Important | 9 | 6 | 1.5 | 3 | 7. WSJF is calculated the order of development is calculated automatically
9. Labels are missing from images | 2 - Some | 2 - Some of the time | 2 - Important | 8 | 16 | 0.5 | 9 | 8. Develop the stories based on the order.
10. Customization of a chat region. Cannot drag into a new position. | 1 - A few or limited user role | 3 - All of the time | 2 - Important | 6 | 24 | 0.25 | 10
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Drop Menus
How Many Users Does It Impact (Scoring: 3 - All, 2 - Some, 1 - A few or a Limited User Role)
3 - All | 3
2 - Some | 2
1 - A few or limited user role | 1
How Often Does It Occur (Scoring: 3 - All of the Time, 2 - Some of the Time, 1 - Infrequently)
3 - All of the time | 3
2 - Some of the time | 2
1 - Infrequently | 1
How Bad is the Problem (Scoring: 4 -Critical, 3 - Severe , 2 - Important, 1 - Not Important)
4 - Critical | 4
3 - Severe | 3
2 - Important | 2
1 - Not Important | 1